## Project Plan
Manufacturer Management Panel
Group Members |  |  | Project Summary
Developer Name | Role |  | It allows a manufacturer to manage the sale of its products to its regular customers. The manufacturer manages orders and payments from its customers. Customers place orders. Employees can also view incoming orders.
Buğra | FullStack
Project Progress |  |  |  | Resources & Budget
Task | Responsible | Deadline | Status | Resource | Cost ($)
Project Requirement Analysis | Buğra | 20.03.2026 | Done | Server Hosting | 50
UI/UX Design | Buğra | 25.03.2026 | In Progress | Domain | 15
Backend API Development | Buğra | 30.03.2026 | To Do | Design Tools | 20
Frontend Development | Buğra | 05.04.2026 | To Do | Testing Tools | 10
Testing | Buğra | 10.04.2026 | To Do | Salary | 9500
Documentation | Buğra | 15.04.2026 | To Do | Total | 9600$
Project Dependencies
ASP.NET MVC (.NET 9)
C#
SQL Server
Razor View Engine
HTML / CSS / JavaScript
Authentication